## Instructions
Agency Profitability Worksheet
Use this workbook to forecast margin before accepting work and to compare the approved plan with actual delivery.
Workflow
1 | Add one row per project on Project P&L.
2 | Enter revenue, planned hours, hourly internal cost, and other direct costs.
3 | Update actual hours and costs weekly; formulas calculate variance and margin.
4 | Use Capacity Plan before accepting new work.
5 | Use Change Impact to price extra work before production begins.
Definitions
Gross margin % | (Revenue − direct cost) ÷ Revenue.
Forecast margin % | (Revenue − forecast direct cost) ÷ Revenue.
Hours variance | Actual hours − planned hours. Positive means over plan.
Change request | Any added deliverable, revision, channel, meeting, or deadline change outside the approved baseline.

## Project P&L
Project ID | Client | Service | Status | Revenue | Planned hours | Actual hours | Internal hourly cost | Other direct cost | Forecast cost | Actual cost | Forecast margin % | Actual margin % | Hours variance | Margin flag | Next action

## Capacity Plan
Team member | Role | Weekly capacity hours | Utilization target % | Committed hours | Reserved ops hours | Available delivery hours | Overallocated?

## Change Impact
Change ID | Project ID | Requested item | Extra hours | Hourly sell rate | Added price | Internal cost | Net contribution | Approval status | Decision date

## Dashboard
Agency Profitability Dashboard
Total revenue | Project | Actual margin %
Forecast direct cost
Actual direct cost
Forecast margin %
Actual margin %
Planned hours
Actual hours
Open change value